## administration
Name (pls rename) | Task types | Status | Instructions:
ARVIND | UML diagram | TODO | Please rename the file and copy the shared link to your repository. Due to academic integrity, failure to do so may result in 0 mark.
RYAN | Design rationale | IN PROGRESS | Put your team members' name in "Name" column (A2-A5)
NHAT QUANG | Discussion | DONE | Please go to another tab below (Assignment 1, 2 or 3)
EVERYONE | Brainstorm | INCOMPLETE | As a team, discuss and list on what tasks that need to be done along with its type.
| Code comment |  | Ideally you'll assign yourself to a task. However, you're welcome to assign a task to someone if everyone agrees on that.
| Code review |  | While working on a task, please change the status from "TODO" to "IN PROGRESS" to inform your team that you are working on that task.
Once you're done, log the date you've completed the task. Feel free to add extra notes if that help your team understands what've you done with the task. Ideally you'll write a brief reflection on the completed task.
Ideally a task need to be atomic (only one thing), so it shouldn't be shared/done by two people except as a whole "Team discussion".
In a case that you're unable to complete the task and it will be taking over by someone else, set the status to INCOMPLETE, and create a fresh new log with new planning date and contributor's name.
Feel free to add more contribution types if you think they are insufficient
Your markers may have a look at the Version History to make decisions if there are imbalance of contributions. So, please notify your lab demonstrators if that's the case.

## Assignment 1
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First meeeting discussion | Discussion | 2023-03-18 | EVERYONE | DONE | 2022-07-19 | We had a 1 hour meeting to read the assignment specifications together and distributed work equally among team members. The team agreed to have...
Requirement 2 Trader |  |  | RYAN | TODO
First rough draft of student 2 roles as stated on ed strategies | Brainstorm | 2023-03-19 | NHAT QUANG | DONE |  | Brainstorming and working from scratch, meeting on Tuesday applied will be for discussing rationale how to best merge the 3 drafts. Assigned roles: R1: Environment, R2: Trader (doing it solo), R3: Section B and C, R5: Skeleton Bandit and Scimitar.
First draft on tasks as student 1 role in task splitting stratergy on ed | Brainstorm | 2023-03-19 | ARVIND | DONE | 2023-03-25
First draft on tasks as team member 3 role as stated on ED. | Brainstorm | 2023-03-21 | RYAN | DONE
Discuss on ideas of how to relate our tasks to the provided game engine | Discussion | 2023-03-21 | EVERYONE | DONE |  | Discussed during applied session on how the game engine works to get a clearer idea on how to incorparate the game engine into our drafts
Post-discussion draft revision for student 2 roles | Brainstorm | 2023-03-25 | NHAT QUANG | DONE |  | Initial draft didn't take into consideration that some base classes were provided by the game engine, next revision will account for that
Finished initial draft and rationale for Requirement 1's environment | UML diagram | 2023-03-25 | NHAT QUANG | DONE | 2023-03-25 | To be reviewed and discuss on 26/03/2023 meeting.
Finished initial draft and rationale for Requirement 2's trader | UML diagram | 2023-03-26 | NHAT QUANG | DONE | 2023-03-26 | To be reviewed and discuss on 26/03/2023 meeting
26/03/2023 Meeting | Discussion | 2023-03-26 | EVERYONE | DONE | 2023-03-26 | Discussed on a more appropriate task splitting strategy. Reviewed approach and made some changes to initial idea
02/04/2023 Meeting | Discussion | 2023-04-02 | EVERYONE | DONE | 2023-04-02 | Revised and explained every member's approach so that the whole team is on track with each other's ideas. Made some revision as note on the diagram. Assigned work on the beautification of the diagram and starting on design rationale
Add enemies for req 1 | UML diagram | 2023-03-25 | ARVIND | DONE | 2023-03-25
Add Rune for req 2 | UML diagram | 2023-03-26 | ARVIND | DONE | 2023-03-26
Add reset capabilities for req 3 | UML diagram | 2023-03-26 | ARVIND | DONE | 2023-03-26
Add enemies for req 5 | UML diagram | 2023-03-30 | ARVIND | DONE | 2023-03-30
Add resettable enemies to req 3 | UML diagram | 2023-04-01 | ARVIND | DONE | 2023-04-01
Beautify req 3 UML | UML diagram | 2023-03-02 | ARVIND | DONE | 2023-03-02
Beautify req 2 UML | UML diagram | 2023-03-02 | ARVIND | DONE | 2023-03-02
Design rationale for req 2 | Design rationale | 2023-03-03 | ARVIND | DONE | 2023-04-14
Design rationale for req 3 | Design rationale | 2023-03-04 | ARVIND | DONE | 2023-04-14
Design rationale for req 5 | Design rationale | 2023-03-05 | ARVIND | DONE | 2023-04-14
Add enum for req 4 | UML diagram | 2023-04-20 | RYAN | DONE | 2023-04-20
Fixed enum to ArchetypeManager for req 4 | UML diagram | 2023-04-20 | RYAN | DONE | 2023-04-20
Beautify req 4 UML | UML diagram | 2023-03-26 | RYAN | DONE | 2023-03-26
Design rationale for req 4 | Design rationale | 2023-04-14 | RYAN | DONE | 2023-04-12
Clean up and spot errors in req 1 | Code review | 2023-04-07 | RYAN | DONE | 2023-04-07
Re designed Requirement 1's to be more readable | UML diagram | 2023-04-04 | NHAT QUANG | DONE | 2023-04-04
Added Rationale for Requirement 1 Environments | Design rationale | 2023-04-05 | NHAT QUANG | DONE | 2023-04-05
Added Rationale for Requirement 1 Enemies | Design rationale | 2023-04-06 | NHAT QUANG | DONE | 2023-04-06
Re designed Requirement 5's Scimitar and Bandit Skeletion | UML diagram | 2023-04-05 | NHAT QUANG | DONE | 2023-04-05
Added rationale for Scimitar and Grossmesser special attack | Design rationale | 2023-04-06 | NHAT QUANG | DONE | 2023-04-06
Added rationale for Bandit Skeletion design | Design rationale | 2023-04-07 | NHAT QUANG | DONE | 2023-04-07

## Assignment 2
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes

## Assignment 3
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes